## Pinrang
AQUACULTURE IMPROVEMENT PROJECT (AIP)
PINRANG-SOUTH SULAWESI-INDONESIA
No | WORKPLAN | LEAD AGENCY | STAKEHOLDERS | 2023 |  |  |  | 2024 |  |  |  | 2025
|  |  |  | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec) | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec) | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec)
1. Assessment of the ASIC Shrimp protocol in the cultivation chain.
1.1 | Asessment menggunakan protokol ASIC di Hatchery & Nursery | PT. ATINA, ASIC, | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group, Hatchery, Nursery Government: Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff.
1.2 | Improved ASIC protocol assessment results` (Hatchery & Nursery) | PT. ATINA, ASIC, | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group, Hatchery, Nursery Government: Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff.
1.3 | ASIC standard certificate | ASIC | PT. ATINA, ASIC,
1.4 | Re Audit for ASIC standard | PT. ATINA, ASIC, | PT. ATINA, ASIC, KOIN NGO, Farmer group, Hatchery, Nursery
2. Develop and implement an AIP work plan using recommendations for improvement from the assessment results
2.1 | Aquaculture SOP training using ASIC protocol | PT. ATINA, ASIC, | PT. ATINA, ASIC, KOIN NGO, Farmer group, Hatchery, Nursery Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff
2.2 | Farm demonstration and field class training for farmers using the ASIC protocol | PT. ATINA, ASIC, PANDU NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff, Hassanudin Univercity
2.3 | Standard social training for farmers and aquaculture workers with ASIC protocol | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff
2.4 | Encouraging Women's Economic Empowerment for farming communities | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group. Government: Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff
2.5 | Improvement in the tiger shrimp hatchery chain (Nursery Farm) | PT. ATINA, PANDU NGO | PT. ATINA, ASIC, PANDU NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of Pinrang prefecture, Hassanudin Univercity of Makassar
2.6 | Making Nursery Farm SOPs | PT. ATINA, PANDU NGO | PT. ATINA, ASIC, PANDU NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of Pinrang prefecture
3. Climate Change Adaptation
3.1 | Pond Cluster with Aquaculture Practices using ASIC protocol | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group, Hatchery, Nursery Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of South Sulawesi Province, Fisheries Office of pinrang prefecture, Pinrang Aquaculture Extension staff.
3.2 | Group and stakeholder discussion for productivity improvement and climate change resilience with ASIC protocol | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group, Hatchery, Nursery Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of South Sulawesi Province, Fisheries Office of Ppinrang prefecture, Pinrang Aquaculture Extension staff; Surabaya Climate Agency
3.3 |  | PT. ATINA KOIN NGO, BMKG (Climate agency) | PT. ATINA, ASIC, KOIN NGO, Farmer group, Hatchery, Nursery Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of South Sulawesi Province, Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff; Makassar Climate Agency
3.3. | Repair of water channels to ponds | Fisheries Office of Pinrang prefecture | PT. ATINA, PANDU NGO, Farmer group, Government: Fisheries Office of Ppinrang prefecture, Pinrang Aquaculture Extension staff; Surabaya Climate Agency
4. Collaboration with stakeholders
4.1 | Agreement with stakeholder | PT. ATINA, | Hassanudin Univercity of Makassar
Completed
On-Going
Not completed