## Sidoarjo
AQUACULTURE IMPROVEMENT PROJECT (AIP)
SIDOARJO- EAST JAVA -INDONESIA
No | WORKPLAN | LEAD AGENCY | STAKEHOLDERS | 2023 |  |  |  | 2024 |  |  |  | 2025
|  |  |  | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec) | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec) | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec)
1. Assessment of the ASIC Shrimp protocol in the cultivation chain.
1.1 | Farms assessment using ASIC protocol | PT. ATINA, ASIC, | PT. ATINA, ASIC,, KOIN NGO, Government: Aquaculture Extension staff, Fisheries Office of Sidoarjo prefecture,
1.2 | Improved ASIC protocol assessment results` (Farms) | PT. ATINA, ASIC | PT. ATINA, ASIC, KOIN NGO, Hatchery
1.3 | Re Audit for ASIC standard | PT. ATINA, ASIC, | PT. ATINA, ASIC, KOIN NGO, Farmer group, Hatchery, Nursery
1.4 | Improved ASIC protocol assessment results` (Hatchery & Nursery) | PT. ATINA, ASIC, | PT. ATINA, ASIC, KOIN NGO
1.5 | ASIC standard certificate | PT. ATINA, ASIC, | PT. ATINA, ASIC, KOIN NGO
2. Develop and implement an AIP work plan using recommendations for improvement from the assessment results
2.1 | Aquaculture SOP training using ASIC protocol | PT. ATINA, ASIC, | PT. ATINA, ASIC, KOIN NGO, Farmer group, Hatchery, Nursery Government: Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of Sidoarjo prefecture,Fisheries Office of East java Province, Sidoarjo Aquaculture Extension staff
2.2 | Farm demonstration and field class training for farmers using the ASIC protocol | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff
2.3 | Standard social training for farmers and aquaculture workers with ASIC protocol | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff
2.4 | Encouraging Women's Economic Empowerment for farming communities | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff
2.5 | Improvement in the tiger shrimp hatchery chain (Nursery Farm) | PT. ATINA, | PT. ATINA, ASIC, KOIN NGO, Farmer group, Hatchery, Nursery. Government: Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of Sidoarjo prefecture,Fisheries Office of East java Province
2.6 | Making Nursery Farm SOPs | PT. ATINA, | PT. ATINA, ASIC, KOIN NGO, Farmer group, Hatchery, Nursery. Government: Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of Sidoarjo prefecture,Fisheries Office of East java Province
2.7 | Identify tiger prawn broodstock | PT. ATINA, | PT. ATINA, ASIC, KOIN NGO,, Hatchery, Government: Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of Sidoarjo prefecture,
3. Climate Change Adaptation
3.1 | Pond Cluster with Aquaculture Practices using ASIC protocol | PT. ATINA, KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of East java Province, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff; Surabaya Climate Agency
3.2 | Group and stakeholder discussion for productivity improvement and climate change resilience with ASIC protocol | PT. ATINA, | PT. ATINA, ASIC,KOIN NGO, Farmer group, Hatchery, Nursery. Government: Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of East java Province, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff; Surabaya Climate Agency
3.3 | Making Cultivation schedule every year based on climate change projection | PT. ATINA KOIN NGO, BMKG(Climate agency) | PT. ATINA, ASIC, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of East java Province, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff; Surabaya Climate Agency
4. Collaboration with stakeholders
4.1 | Climate adaptation field school | PT. ATINA , KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group, Government Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of East java Province, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff; Surabaya Climate Agency, PSDA East Java
4.2. | Monitoring water quality system | PT. ATINA, | PT. ATINA, ASIC, KOIN NGO, Farmer group, Surabaya State University (UNESA)
4.3 | Biota analysis, water and soil quality to increase productivity | PT. ATINA, | PT. ATINA, ASIC, KOIN NGO, Farmer group, Airlangga State University Surabaya (UNAIR)
4.4 | Agreement with stakeholder | PT. ATINA, | Surabaya State University (UNESA), Airlangga State University Surabaya (UNAIR)
4.5 | Employment insurance for pond workers (BPJS-TK) | PT. ATINA, | BPJS-TK
Completed
On-Going
Not completed