## AIP-ASC
Situbondo AIP 2021-2022
Activity |  | Note | Status | YEAR 2021 | [26 empty] | YEAR 2022
|  |  |  | 2021-06-01 |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  | 2021-11-01 |  |  |  | 2021-12-01 |  |  |  | 2022-01-01 |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  | 2022-11-01 |  |  |  | 2022-12-01
|  |  |  | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
AIP-ASC Program
1. On-ground team deployment | bar: 2021-08-01 W4
2. Stakeholder engagement initiation | bar: 2021-08-01 W4 to 2021-10-01 W3
3. Stakeholder meeting (kick-off, quarterly meeting with packers, AIP farmer representatives) | bar: 2021-10-01 W3; 2022-03-01 W4; 2022-06-01 W4; 2022-09-01 W4; 2022-12-01 W2
4. AIP2ASC
- registration | bar: 2021-10-01 W4 to 2021-12-01 W2; 2022-01-01 W1 to 2022-03-01 W4
- gap analysis | bar: 2022-01-01 W1 to 2022-03-01 W4
-improvement plan development | bar: 2022-02-01 W1 to 2022-04-01 W4
5. Training/workshop/seminar
- Farmer training/workshops/seminar: teknis budidaya, administrasi, legalitas, pelatihan K3, pelatihan laboran | bar: 2022-01-01 W2; 2022-02-01 W2; 2022-03-01 W2; 2022-06-01 W1; 2022-07-01 W1; 2022-08-01 W1; 2022-09-01 W1; 2022-10-01 W1; 2022-11-01 W1
- Water quality monitoring research | bar: 2021-11-01 W2; 2021-11-01 W4; 2021-12-01 W2; 2021-12-01 W4; 2022-01-01 W2; 2022-01-01 W4; 2022-02-01 W2; 2022-02-01 W4; 2022-03-01 W2; 2022-03-01 W4; 2022-04-01 W2; 2022-04-01 W4; 2022-05-01 W2; 2022-05-01 W4; 2022-06-01 W2; 2022-06-01 W4; 2022-07-01 W2; 2022-07-01 W4; 2022-08-01 W2; 2022-08-01 W4; 2022-09-01 W2; 2022-09-01 W4; 2022-10-01 W2; 2022-10-01 W4; 2022-11-01 W2; 2022-11-01 W4; 2022-12-01 W2; 2022-12-01 W4
- SCI national agenda | bar: 2022-04-01 W1
Eid Al Fitr (religious holiday)