## Sidoarjo (update 2026)
AQUACULTURE IMPROVEMENT PROJECT (AIP)
SIDOARJO- EAST JAVA -INDONESIA
No | WORKPLAN | LEAD AGENCY | STAKEHOLDERS | 2026 |  |  |  | 2027 |  |  |  | 2028
|  |  |  | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec) | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec) | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec)
1. Assessment of the ASIC Shrimp protocol in the cultivation chain.
1.1 | Re Audit for ASIC standard | PT. ATINA, ASIC | PT. ATINA, ASIC, Farmer group, Hatchery, Nursery
2. Develop and implement an AIP work plan using recommendations for improvement from the assessment results
2.1 | Aquaculture SOP training standard | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of East java Province, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff; Surabaya Climate Agency
2.2 | Farm demonstration and field class training for farmers using the ATINA standard | PT. ATINA, KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group. Government: Balai Besar Perikanan Budidaya Air Payau Jepara, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff
2.3 | Standard social training for farmers and aquaculture for farm manager using the ATINA standard | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, KOIN NGO, Farmer group. Government: Balai Besar Perikanan Budidaya Air Payau Jepara, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff
2.4 | Women's Economic Empowerment for farming communities | PT. ATINA, ASIC, KOIN NGO | PT. ATIN, KOIN NGO, Farmer group. Government: Balai Besar Perikanan Budidaya Air Payau Jepara, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff
2.6 | Identify tiger prawn broodstock | PT. ATINA | PT. ATINA, Hatchery, Government: Balai Besar Perikanan Budidaya Air Payau Jepara, Fisheries Office of Sidoarjo prefecture,
3. Climate Change Adaptation
3.1 | Pond Cluster with Aquaculture Practices using ATINA standard | PT. ATINA, KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group. Government: Balai Besar Perikanan Budidaya Air Payau Jepara, Fisheries Office of East java Province, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff; Surabaya Climate Agency
3.2 | Cultivation schedule every year based on climate change projection | PT. ATINA KOIN NGO, BMKG(Climate agency) | PT. ATINA, ASIC, KOIN NGO, Farmer group. Government: Balai Besar Perikanan Budidaya Air Payau Jepara, Fisheries Office of East java Province, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff; Surabaya Climate Agency
3.3 | Nursery & Mangrove planting | PT. ATINA, KOIN NGO | PT. ATINA, KOIN NGO, Farmer group, Fisheries Office of East java Province, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff
4. Collaboration with stakeholders
4.1 | Climate adaptation field school | PT. ATINA , KOIN NGO | PT. ATINA, ASIC, KOIN NGO, Farmer group, Government Balai Perikanan Budidaya Air Payau Jepara, Fisheries Office of East java Province, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff; Surabaya Climate Agency
4.2 | Operating procedures for farm drainage | PT. ATINA, PUSDA East Java | PT. ATINA, Farmer group, Fisheries Office of East java Province, Fisheries Office of Sidoarjo prefecture, Sidoarjo Aquaculture Extension staff; Surabaya Climate Agency, PUSDA East Java
4.3 | Employment insurance for pond workers (BPJS-TK) | PT. ATINA | PT. ATINA, BPJS-TK, farmer group
Completed
On-Going
Not completed