## AIP 2026 2028
AQUACULTURE IMPROVEMENT PROJECT (AIP)
BRAGANCA - PARA - BRAZIL
No | WORKPLAN | LEAD AGENCY | STAKEHOLDERS | 2026 |  |  |  | 2027 |  |  |  | 2028
|  |  |  | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec) | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec) | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec)
1. Assessment of the Pirarucu (Arapaimas gigas) cluster from Gpesca Company under ASC and BAP Farm Standards
1.1 | Self evaluation Audit under ASC Farm standard | Netuno USA | Netuno USA, Gpesca, IABS
1.2 | Self evaluation Audit under BAP Farm standard | Netuno USA | Netuno USA, Gpesca, IABS
2. Develop and implement an AIP work plan using recommendations for improvement from the self evaluation ASC/BAP standards
2.1 | Legal compliance documentation segregation | Gpesca | Netuno USA, Gpesca
2.2 | Management System Selection and Implementation | Gpesca | Netuno USA, Gpesca
2.3 | PCMSO - Business Ethics Revision and Adaptation | Gpesca | Netuno USA,Gpesca, IABS
2.4 | Treceability and Disclosure System Revision and Update | Gpesca | Netuno USA,Gpesca, IABS
2.5 | Supply Chain - Encourage Fingerlings suppliers in Para State to also adopt ASC standard | GPesca | Netuno USA, Gpesca
2.6 | Environmental Risk Assessment (Ecological Important Habitats, Wildlife Interaction, Escapes and Biosecurity, Soil Salinisation, Natural Resources and Energy use, Waste and Pollution evatuation) | IABS | Netuno USA,Gpesca, UFPA
2.7 | Water Quality Program (start collecting and recording water quality paramethers as required for the standards) | GPesca | Netuno USA, Gpesca
3. Changing from Processing Plant Byproducts to Formulated Dry Feed
3.1 | Discuss with Standards Directory for Standard and Science about processes that can assure both food safety, nutritional and less environmental impact for the by product from Gpesca processing plant facility | Netuno USA | Netuno USA, Gpesca
3.2 | Run comparative tests (by product Gpesca processing facility) x Carnivor Dry Pellet Feed | Netuno USA | Gpesca, Netuno USA, IABS, UFPA
3.3 | Spread Knowledge generated in 3.2 test to all farming facilities | GPesca | Gpesca, UFPA and IABS
4. Standard Selection and Preparation for Full Audit
4.1 | Human Rights & Workers Rights | GPesca | Gpesca, Netuno USA
4.2 | Animal health & welfare | GPesca | Gpesca, Netuno USA, IABS, UFPA
4.3 | Full Audit under the selected Standard | Gpesca | Netuno USA, Gpesca, IABS
Completed
On-Going
Not completed