## SouthSulawesi
AIP PROGRAM
PINRANG AREA
WORKPLAN |  | LEAD AGENCY | STAKEHOLDERS | 2022 |  |  |  | 2023 |  |  |  | 2024
|  |  |  | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec) | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec) | Q1 (Jan - Marc) | Q2 (Apr-June) | Q3 (July-Sept) | Q4 (Oct-Dec)
1. Assessment of the ASIC Shrimp protocol in the cultivation chain.
1.1 | Farms assessment using ASIC protocol | PT. ATINA, ASIC, | PT. ATINA, ASIC, OXFAM, KOIN NGO, Government: Aquaculture Extension staff, Fisheries Office of Pinrang prefecture,
1.2 | Improved ASIC protocol assessment results` (Farms) | PT. ATINA, ASIC | PT. ATINA, ASIC, OXFAM, KOIN NGO, Hatchery
1.3 | Pre-Assessment menggunakan protokol ASIC di Hatchery & Nursery | PT. ATINA, ASIC, | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group, Hatchery, Nursery Government: Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff.
1.4 | Improved ASIC protocol assessment results` (Hatchery & Nursery) | PT. ATINA, ASIC, | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group, Hatchery, Nursery Government: Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff.
1.5 | ASIC standard certificate | ASIC | PT. ATINA, ASIC,
2. Develop and implement an AIP work plan using recommendations for improvement from the assessment results
2.1 | Aquaculture SOP training using ASIC protocol | PT. ATINA, ASIC, | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group, Hatchery, Nursery Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of Pinrang prefecture,Fisheries Office of South Sulawesi Province, Pinrang Aquaculture Extension staff
2.2 | Farm demonstration and field class training for farmers using the ASIC protocol | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff
2.3 | Standard social training for farmers and aquaculture workers with ASIC protocol | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff
2.4 | Encouraging Women's Economic Empowerment for farming communities | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of Pinrang prefecture, Pinrang Aquaculture Extension staff
2.5 | Improvement in the tiger shrimp hatchery chain (Nursery Farm) | PT. ATINA, | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of Pinrang prefecture
2.6 | Making Nursery Farm SOPs | PT. ATINA, | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group. Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of Pinrang prefecture
4. Climate Change Adaptation
4.1 | Pond Cluster with Aquaculture Practices using ASIC protocol | PT. ATINA, ASIC, KOIN NGO | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group, Hatchery, Nursery Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of South Sulawesi Province, Fisheries Office of Ppinrang prefecture, Pinrang Aquaculture Extension staff; Surabaya Climate Agency
4.2 | Group and stakeholder discussion for productivity improvement and climate change resilience with ASIC protocol |  | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group, Hatchery, Nursery Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of South Sulawesi Province, Fisheries Office of Ppinrang prefecture, Pinrang Aquaculture Extension staff; Surabaya Climate Agency
4.3 | Making Cultivation schedule every year based on climate change projection |  | PT. ATINA, ASIC, OXFAM, KOIN NGO, Farmer group, Hatchery, Nursery Government: Balai Perikanan Budidaya Air Payau Takalar, Fisheries Office of South Sulawesi Province, Fisheries Office of Ppinrang prefecture, Pinrang Aquaculture Extension staff; Surabaya Climate Agency
5. Changes in management practices/policies, Third Party Verification
5.1 | 3rd party verification | ASIC, WFCF | PT. ATINA, NGO, ASIC, WFCF
Completed
On-Going
Not completed